## Sheet1
Stages
Staff | Planning | Designing | Developing | Testing | Implementing | Total
| (3 months) | (3 months) | (3 months) | (1 week) | (3 days) | Time
Choose a project | 4 Days / 10 hours
Brainstorming | 3 Days / 7 hours
Create project proposal | 2 Days / 2 hours
Look for a client | 3 Days / 2 hours
Submit letter of request for interview to the client | 1 Day / 1 hour
Conduct Interview | 1 Day / 1 hour
Create pitch video | 5 Days / 3 hours
Get adviser/ consultant | 1 Day / 1 hour
Total Days and Hours of Planning | [5 empty] | 20 Days / 28 hours
Create wiki |  | 2 Days / 6 hours
Create github |  | 2 Days / 6 hours
Create documentation |  | 2 Days / 2 hours
Technical Background |  | 4 Days / 5 hours
Software Requirement Specification |  | 4 Days / 7 hours
Create diagrams |  | 20 Days / 50 hours
Create progress report |  | 15 Days / 12 hours
Gantt Chart |  | 7 Days / 10 hours
Project Charter |  | 5 Days / 4 hours
Scope of work |  | 7 Days / 7 hours
Vision and scope document |  | 5 Days / 10 hours
Submission of deliverables |  | 5 Days / 8 hours
Meet the adviser |  | 1 Day / 2 hours
Revise documentation |  | 4 Days / 28 hours
Revise Diagrams |  | 4 Days / 20 hours
Update wiki and git |  | 2 Days / 7 hours
Total of days and hours of Designing | [5 empty] | 89 Days / 184 hours
Mobile Application Development |  |  | 30 days / 100 hours
Software Testing and Quality |  |  |  | 3 days / 4 hours
Implementation |  |  |  |  | 1 Day / 3 hours
[5 empty] | Total of All: | 143 Days / 323 hours